## Slide 1
M&A Day 1 Communications Plan
Day One Welcome Experience for Acquired Co.
Day One Leadership Presence
Day One Communication to Acquirer Employees
Day One Website
Plan
Day One Stakeholder Outreach
Day One Expectation
Setting
Communicate ahead of time what people can expect to “work” on Day One and what will come later
Coordinate closely with other teams to accurately capture Day One objectives
  Email
  Intranet Access
  Policies
Articulate what will “not” change
  Pay & Benefits
  Process for paying vendors
  Process for submitting expenses
This forms the basis of how people will measure our Day One success
Welcome Packets
  Message from CEO
  Company Vision
  Safety Overview (light touch)
  Basic FAQs
  New Company Infographic
  Acquirer Swag
  Checklist
  What to expect in coming weeks
    Email structure
    IT Access
    Stationery order
    FAQ process
    Pay & Benefits reminder
  Site Essentials
  Temporary Signage
  How to order signs, decals, vision posters
President & CEO
CEO will begin one-week road trip & close tour with video webcast employee forum from corporate
SC Leaders
  CEO will be at headquarters
  VPs hold conference calls with their teams
  Functional leads hold conference calls with their teams
  Other Leaders
  SC to communicate that site leaders should take time to acknowledge Day One with their local teams
Newsletter on Day One
Message from CEO (also send on email)
Updated infographic about the combined company
FAQ Hub
Explore Acquirer story
Link to news release
Newsletter in Week One
CEO blogs from the road trip
CEO employee forum video (after road trip ends)
Target
Splash page that replaces home page with announcement that we are now Newco
Links to critical business pages
  Access
  Contacts
  TBD
Acquirer
Welcome pop-up page for visitors coming from target.com
Update spotlight with Day One news & link to news release
Incorporate critical information in investor section
Elected officials (Federal, State, City)
Philanthropic relationships (from Target)
Customers
Contractors
Suppliers
Media Relations Plan
MergerIntegration.com
© PRITCHETT, LP
800-992-5922