## Slide 1
Operations
Sales
R&D
Finance
Information Technology
Human Resources
Corporate
Legal
INTEGRATION MANAGEMENT OFFICE (IMO)
STEERING COMMITTEE (SC)
Senior leadership approves plans and provides guidance
Coordinates teams, sets pace, prioritizes work, brings methodology, and manages interdependencies
Integration Manager | Communications Lead
ALL functional areas being integrated should be represented.
Typical Integration Teams
Leaders of functional teams develop and execute plans in their areas. Two leads, one from each company,
for each workstream.

## Slide 2
Establishing an IMO for the purposes of managing integration is highly recommended, as it provides a “home base” for all integration activities. It can be set up as a unique cost center to capture integration-related expenses.
Responsibilities
Drives development of the overall integration plan including all the integration projects, communication plans, and achievement of synergy beneﬁts
Deﬁnes and manages your integration processes including functional work plan reviews, cross-functional collaborations, issue management plans, and executive status updates
Manages stakeholder communication including lists of company executives, functional resource owners, and acquired company managers
Drives the pace of integration and tackles “ad hoc” issues
Tracks continuous improvements such as measuring and surveying various areas, incorporating feedback into updated integration processes and tools, etc.
Integration Management Office

## Slide 3
Responsibilities
Serve as Integration Lead of the respective functional (time commitment will vary by the size and complexity of the integration)
Develop, track, and report functional work plan progress and issues to the IMO
Ensure completion and adherence to the scope identified in the Integration Project Charter
Plan and coordinate overall activities for a specific function
Participate in integration planning process, and use IMO tools for tracking and communicating information regarding integration activities
Is point of contact for the IMO as well as its peer functions and the acquired company
Escalates integration-related issues within their function
Ensures consistency between intra-function status reporting and integration reporting
Supports project, synergy, and communication planning and execution
The Functional Integration / Workstream Team Lead is a focal point for accomplishing all functional work, including development of integration work plans, issue management, documentation, and integration closing activities.
Functional Integration Team Leads